## Instructions
Using the Status tracker
At the end of each week, update the status of all activities completed during the week
The status tracker shown in this worksheet is an example tracker (values filled are during the middle of the week)
Fill in hours spent on each activity during the current week
If 5 team members each spent an hour, that counts as 5 hours
Fill in time for activities not fully completed ("ongoing") as well, then update these values during following weeks
During the planning phases, identify the activities to be done during each week
If you spend time on an activity not listed in the tracker, add the activity and list actual hours (need not fill in estimated hours if you didn't estimate it up front)
For new activities, identify the type of activity - documentation, coordination, estimation etc.
At the end of each week, plan ahead for the following week
Identify people responsible for each activity
Estimate the hours needed for the activity
TEAM NAME | (TEAM NUMBER 1)
PROJECT NAME | (ASAP)
PROJECT MENTOR | (Dr. Sridhar Chimalakonda)
TEAM MEMBERS | Nakshatra Gupta (CS17B020)
K S Koushik (CS17B013)
Ashutosh Rajput (CS17B007)

## Team_Status_Sample
TEAM NAME | (TEAM NUMBER 1)
PROJECT NAME | (ASAP)
PROJECT MENTOR | (Dr. Sridhar Chimalakonda)
Activity Name | Type | Responsible | Estimated Team Hours | Actual Hours | Status | Comments | Estimation error | Estimation error %
See Instructions sheet for usage
Week 1 (sept 5- sept 11)
Learn React | Preparation | ALL | 2 | 2.5 | Done | Using YouTube tutorials, and previous html knowledge helped a big deal | -0.5 | 20
Learn Bootstrap | Preparation | Koushik, Ashutosh | 0.5 | 0.4 | Done | The official documentation of bootstrap was fairly enough for learning it and also previous css knowledge helped. | 0.1 | 25
Learn Basic Backend database management | Preparation | Nakshatra | 3 | 2.5 | Done | Youtube tutorials used. | 0.5 | 20
Git Repository Setup | Preparation | ALL | 0.5 | 1.5 | Done
Made the user stories for our Web Application | Requirements | ALL | 1.5 | 0 | Done | Made using the ideas given in the class | 1.5
Degined the GUI for the web Application | Development | Koushik, Ashutosh | 24 | 20 | Done | Both of us divided the work and generated separate components and pages for the GUI | 4 | 20
We implemented signup and stored the user data in a database. | Development | Nakshatra | 22 | 24 | Done | Learnt the use of Mongodb and implemented the signup data posting innthe database | -2 | 8.3333
Status tracker | Documentation | Ashutosh, Koushik | 1 | 1 | Done | Wrote a log of all the activities done in this week | 0 | 0
Week 7 (sept 12 - sept 18)
Week 8 (sept 19 - sept 25)
Week 9
Week 10
Week 11
Week 12
Week 13
Week 14
Week 15
Week 16
Week 17

## Individual_Status
TEAM NAME | (TEAM NUMBER 1)
PROJECT NAME | (ASAP)
PROJECT MENTOR | (Dr. Sridhar Chimalakonda)
Actvities | Nakshatra Gupta (CS17B020) |  | K S Koushik (CS17B013) |  | Ashutosh Rajput (CS17B007) |  | Estimated Total Hours | Actual Total Hours
| Estimated Time | Actual Time Spent | Estimated Time | Actual Time Spent | Estimated Time | Actual Time Spent
Week 4 - (Aug 21 - Aug 28 )
Learrn React | 3 | 3.5 | 3 | 3.5 | 3 | 3.5 | 9 | 10.5
Learn Bootstrap |  |  | 1 | 0.75 | 1 | 0.75 | 2 | 1.5
Learn Basic Backend database management | 10 | 12
Git Repository Setup | 1 | 2 | 1 | 0.5 | 1 | 0.5 | 3 | 3
Made the user stories for our Web Application | 1 | 1 | 1 | 1 | 1 | 1 | 3 | 3
Degined the GUI for the web Application |  |  | 20 | 24 | 20 | 24 | 40 | 48
We implemented signup and stored the user data in a database. | 11 | 13 | 3 | 6 |  |  | 14 | 19
Status tracker | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 1.5 | 1.5
Week 7 (sept 12 - sept 18) | 26.5 | 32 | 29.5 | 36.25 | 26.5 | 30.25 | 82.5 | 98.5
[7 empty] | 0 | 0
[7 empty] | 0 | 0
[7 empty] | 0 | 0
[9 empty] | 0 | 0
[9 empty] | 0 | 0
[9 empty] | 0 | 0
[9 empty] | 0 | 0
[9 empty] | 0 | 0
[9 empty] | 0 | 0
[9 empty] | 0 | 0
[9 empty] | 0 | 0
[9 empty] | 0 | 0
[9 empty] | 0 | 0
[9 empty] | 0 | 0
[9 empty] | 0 | 0
[9 empty] | 0 | 0
[9 empty] | 0 | 0
[9 empty] | 0 | 0
[9 empty] | 0 | 0
[9 empty] | 0 | 0
[9 empty] | 0 | 0
[9 empty] | 0 | 0
[9 empty] | 0 | 0
[9 empty] | 0 | 0
[9 empty] | 0 | 0
[9 empty] | 0 | 0
[9 empty] | 0 | 0
[9 empty] | 0 | 0
[9 empty] | 0 | 0
[9 empty] | 0 | 0
[9 empty] | 0 | 0
[9 empty] | 0 | 0
[9 empty] | 0 | 0
[9 empty] | 0 | 0
[9 empty] | 0 | 0
[9 empty] | 0 | 0
[9 empty] | 0 | 0
[9 empty] | 0 | 0
[9 empty] | 0 | 0
[9 empty] | 0 | 0
[9 empty] | 0 | 0
[9 empty] | 0 | 0
[9 empty] | 0 | 0
[9 empty] | 0 | 0
[9 empty] | 0 | 0
[9 empty] | 0 | 0
[9 empty] | 0 | 0
[9 empty] | 0 | 0
[9 empty] | 0 | 0
[9 empty] | 0 | 0
[9 empty] | 0 | 0
[9 empty] | 0 | 0
[9 empty] | 0 | 0
[9 empty] | 0 | 0
[9 empty] | 0 | 0
[9 empty] | 0 | 0
[9 empty] | 0 | 0
[9 empty] | 0 | 0
[9 empty] | 0 | 0
[9 empty] | 0 | 0
[9 empty] | 0 | 0
[9 empty] | 0 | 0
[9 empty] | 0 | 0
[9 empty] | 0 | 0
[9 empty] | 0 | 0
[9 empty] | 0 | 0
[9 empty] | 0 | 0
[9 empty] | 0 | 0
[9 empty] | 0 | 0
[9 empty] | 0 | 0
[9 empty] | 0 | 0
[9 empty] | 0 | 0
[9 empty] | 0 | 0
[9 empty] | 0 | 0
[9 empty] | 0 | 0
[9 empty] | 0 | 0
[9 empty] | 0 | 0
[9 empty] | 0 | 0
[9 empty] | 0 | 0
[9 empty] | 0 | 0
[9 empty] | 0 | 0
[9 empty] | 0 | 0
[9 empty] | 0 | 0
[9 empty] | 0 | 0
[9 empty] | 0 | 0
[9 empty] | 0 | 0
[9 empty] | 0 | 0
[9 empty] | 0 | 0
[9 empty] | 0 | 0
[9 empty] | 0 | 0
[9 empty] | 0 | 0
[9 empty] | 0 | 0
[9 empty] | 0 | 0
[9 empty] | 0 | 0
[9 empty] | 0 | 0
[9 empty] | 0 | 0
[9 empty] | 0 | 0
[9 empty] | 0 | 0
[9 empty] | 0 | 0
[9 empty] | 0 | 0
[9 empty] | 0 | 0
[9 empty] | 0 | 0
[9 empty] | 0 | 0
[9 empty] | 0 | 0
[9 empty] | 0 | 0
[9 empty] | 0 | 0
[9 empty] | 0 | 0
[9 empty] | 0 | 0
[9 empty] | 0 | 0
[9 empty] | 0 | 0
[9 empty] | 0 | 0
[9 empty] | 0 | 0
[9 empty] | 0 | 0
[9 empty] | 0 | 0
[9 empty] | 0 | 0
[9 empty] | 0 | 0
[9 empty] | 0 | 0
[9 empty] | 0 | 0
[9 empty] | 0 | 0
[9 empty] | 0 | 0
[9 empty] | 0 | 0
[9 empty] | 0 | 0
[9 empty] | 0 | 0
[9 empty] | 0 | 0
[9 empty] | 0 | 0
[9 empty] | 0 | 0
[9 empty] | 0 | 0
[9 empty] | 0 | 0
[9 empty] | 0 | 0
[9 empty] | 0 | 0
[9 empty] | 0 | 0
[9 empty] | 0 | 0
[9 empty] | 0 | 0